## Instructions
Objective of this exercise:
To create a development plan to evenly distribute the implementation of the use cases over the Contruction Phase
To allocate use cases to each team member for equal work distribution and responsibility
Instructions:
1 | Save file immediately as <your team name> i.e. Team01
2 | Use the Development Schedule worksheet and populate this sheet with the use case numbers - list the use case names & numbers under the heading Use Case Glossary in Column A
3 | The dates indicate when you will have completed the implementation of the use case(s), this will be used for assessment purposes
4 | So if you say that A100 will be done by 7/8 August, we can then test that use case
5 | The data in columns B & N MUST NOT be changed - this is the same for all students and all groups
6 | When scheduling the use cases, try to do the critical ones first and the reports/queries last

## Development Schedule
Use Case Development Schedule 2019
Team Name: Stats and Stacks
|  |  |  | Progress Checks | Progress Checks | Progress Checks | Progress Checks | Progress Checks | Progress Checks | Progress Checks
Team Member | 30/31 Jul | 6/7 Aug | 13/14 Aug | 20/21 Aug | 27/28 Aug | 3/4 Sep | 10/11 Sep | 17/18 Sep | 1/2 Oct | 8/9 Oct | 15/16 Oct | 22/23 Oct | 2019-10-28
Bernard | Database Implementation | A0700 | A1100 | A1500 | A1000 | A1300 | A0800 | A0900 | A1400 | A0600 | A1200 |  | Project Due
Tiffany |  | C0800 | C0300 | C0400 | C0200 | C0900 | C0100 | C1000 | C0500 | C0600 | C0700
Mu'minah |  | B0200 | B0300 | B0400 | A0100 | A0300 | A0200 | B0100 | A0400 | A0500
Use Case Glossary
A0600 | Add challenge to own list
A0700 | Suggest challenge
A0800 | Mark challenge as completed
A0900 | Upload photo
A1000 | View ratings/reviews
A1100 | Rate challenge
A1200 | Send challenge invite
A1500 | View congrats on completed challenge
A1300 | View own challenges
A1400 | View new challenges
C0100 | Send friend request
C0200 | Accept/Reject friend request
C0300 | Remove friend
C0400 | Accept/Reject challenge invite
C0500 | Verify friend’s challenge completion
C0600 | Calculate points
C0700 | Check Achievements
C0800 | View friend’s profile
C0900 | View friend list
C1000 | View friends’ challenges
B0100 | Login/Logout
B0200 | Sign up
B0300 | Maintain account
B0400 | View profile
A0100 | Create challenge
A0200 | Approve/Reject suggested challenge
A0300 | Maintain challenge
A0400 | View established challenges
A0500 | View suggested challenges